# TranslateLab AI

Five Week Machine Translation Research Project Checklist

A practical working document for a 25 day research project. Build an English to German translation MVP early, then use it to run controlled fine-tuning, evaluation and model comparison experiments.

Owner  ________________________________________________

Start date  ________________________________________________

Target finish  ________________________________________________

Repository / project link  ________________________________________________

## Project at a glance

| Duration | Core direction | Research emphasis | Demo |
| --- | --- | --- | --- |
| 5 weeks / 25 workdays | English → German primary; German → English secondary | SFT, domain adaptation, BLEU / chrF / COMET, error analysis, preference signals | Streamlit comparison lab |

## Research question

Can supervised fine-tuning improve English to German translation of technical text, and how does the specialized NMT model compare with a multilingual LLM in translation quality, terminology, generalization and inference efficiency?

## Project goals

☐  Establish reproducible pretrained NMT baselines before fine-tuning.

☐  Compare technical and general-domain performance while protecting held-out test sets.

☐  Run controlled SFT experiments and explain positive, neutral or negative results.

☐  Evaluate with BLEU, chrF and COMET, supported by terminology checks, error analysis and latency.

☐  Compare baseline NMT, fine-tuned NMT and a multilingual LLM; collect a small human preference set.

☐  Deliver a working Streamlit demonstration, research report and interview-ready presentation.

## Role alignment

| Apple role | Evidence this project should show |
| --- | --- |
| Machine Learning Research Engineer, Machine Translation | Transformer / NMT understanding, research questions, controlled experiments, multilingual LLM comparison, rigorous evaluation. |
| AIML Applied Research Engineer, Machine Translation | Supervised fine-tuning, data quality, preference signals, quality regression checks, reproducible applied research. |

Focus allocation: 30% fine-tuning and domain adaptation · 25% evaluation · 20% controlled research · 15% interactive application · 10% tests, documentation and deployment. Keep roughly three quarters of effort on research and evaluation.

# Project controls and acceptance criteria

Working hours / week  ________________________________________________

Primary technical domain  Software documentation (recommended) / _______________________

Compute available  ________________________________________________

Weekly review day  ________________________________________________

## Scope rules

☐  Primary direction: English to German. German to English is secondary if time allows.

☐  Suggested data targets: 10,000 training pairs, 1,000 validation pairs, 1,000 technical test pairs, 500 general test pairs. Treat these as targets; prioritize licensed, well-aligned data.

☐  Keep technical and general test sets out of training and model selection. Record dataset source, license, cleaning, deduplication and split method.

☐  Start with Helsinki-NLP/opus-mt-en-de for the accessible pretrained baseline. Keep E0, E1 and E2 comparable and record the exact checkpoint.

☐  The five-week goal is a credible, reproducible research slice. Results may be negative; report them honestly.

## Acceptance criteria

| Area | Accept when… |
| --- | --- |
| Data | Source and license recorded; splits are disjoint; alignment and cleanup checks are documented; test sets remain held out. |
| Training | At least one domain fine-tuned checkpoint; training config, seed, data version, checkpoint and compute recorded; baseline comparison reproducible. |
| Evaluation | BLEU, chrF and COMET reported on the same held-out examples; technical and general results separated; terminology, errors and latency summarized. |
| Research | At least E0 / E1 / E2 comparison; hypotheses and controls stated; uncertainty / paired comparison discussed; limitations explicit. |
| Preferences | Aim for ~50 blinded pairwise judgments; record source, candidates, winner / tie and reviewer; compare judgments with automatic metric rankings. |
| Demo | Streamlit translates and compares baseline NMT, fine-tuned NMT and LLM when available; displays model identity and latency; dashboard shows evaluation results. |
| Handoff | Repository has setup instructions, reproducible commands, results, model/data notes, tests, report (target 6–10 pages) and 10–15 minute demo deck. |

## Status key

Use ☐ Not started   ◐ In progress   ☑ Done   ! Blocked. Write dates and evidence links next to completed work. Update the milestone status at each weekly review.

Overall status  ☐ Not started   ☐ In progress   ☐ At risk   ☐ Complete

Last updated  ________________________________________________

Current priorities / decisions  ________________________________________________________________________________

________________________________________________________________________________

# Week 1

Foundations, data and first MVP

Week objective: Deliver a working English–German translator and a reproducible baseline benchmark.

Week status  ☐ Not started   ☐ In progress   ☐ At risk   ☐ Complete

Review date  ________________________________________________

Evidence / branch / report link  ________________________________________________

## Day 1  |  Map the task and model

☐  Review encoder-decoder Transformer, attention, tokenization and MarianMT.

☐  Write the project question, hypotheses, scope and first experiment outline.

☐  Create the repository structure and a research notebook.

Deliverable  Research notebook, project brief and repository skeleton

Done when  The task and first hypotheses are written down; notebook runs and is committed.

Notes / blocker  ________________________________________________________________________________

## Day 2  |  Run pretrained translation

☐  Load Helsinki-NLP/opus-mt-en-de using PyTorch and Hugging Face.

☐  Build a repeatable translation function; record model ID, decoding settings and latency.

☐  Check several representative technical sentences manually.

Deliverable  Working EN→DE translation pipeline

Done when  A clean setup can translate a small set of examples and records its configuration.

Notes / blocker  ________________________________________________________________________________

Weekly notes / decisions  ________________________________________________________________________________

## Day 3  |  Ship the first MVP

☐  Build a minimal Streamlit text input and translation output.

☐  Show source, German output, selected model and basic latency.

☐  Capture a short demo or screenshots; log known limitations.

Deliverable  First working Streamlit MVP

Done when  A user can enter English text and see a German translation locally.

Notes / blocker  ________________________________________________________________________________

# Days 4–5

Weekly objective: Deliver a working English–German translator and a reproducible baseline benchmark.

## Day 4  |  Prepare trustworthy data

☐  Select a technical domain and licensed parallel dataset.

☐  Clean, align and deduplicate sentence pairs; inspect a sample manually.

☐  Create train / validation / technical test / general test splits and document the split process.

Deliverable  Validated dataset files and data card

Done when  Counts, source, license, filters and split boundaries are recorded; no held-out examples leak into training.

Notes / blocker  ________________________________________________________________________________

Weekly notes / decisions  ________________________________________________________________________________

## Day 5  |  Measure the baseline

☐  Implement SacreBLEU BLEU and chrF evaluation.

☐  Run the pretrained model on technical and general test sets.

☐  Save predictions, metric configuration and baseline report.

Deliverable  Baseline benchmark report

Done when  Results can be reproduced from saved predictions and exact metric settings.

Notes / blocker  ________________________________________________________________________________

## Week 1 milestone

☐  Working English–German MVP and reproducible baseline results.

Milestone outcome  ☐ Met   ☐ Partially met   ☐ Not met

Carry-forward items  ________________________________________________

# Week 2

Supervised fine-tuning and domain adaptation

Week objective: Train a domain-adapted model and compare controlled data mixtures.

Week status  ☐ Not started   ☐ In progress   ☐ At risk   ☐ Complete

Review date  ________________________________________________

Evidence / branch / report link  ________________________________________________

## Day 6  |  Build the training pipeline

☐  Tokenize train / validation data and check truncation and batch shapes.

☐  Implement the PyTorch / Hugging Face Seq2SeqTrainer pipeline.

☐  Record seed, optimizer, learning rate, batch size, epochs, max length and checkpoint.

Deliverable  Reproducible training code

Done when  A small smoke run starts, validates, saves and reloads a checkpoint.

Notes / blocker  ________________________________________________________________________________

## Day 7  |  Run a small training experiment

☐  Use a small subset to verify the complete training loop.

☐  Inspect loss curves and checkpoint outputs; confirm generation works after reload.

☐  Note local compute limits and decide whether a GPU run is needed.

Deliverable  First fine-tuned model and run log

Done when  Checkpoint reloads and translates; run settings and compute are recorded.

Notes / blocker  ________________________________________________________________________________

Weekly notes / decisions  ________________________________________________________________________________

## Day 8  |  Run controlled fine-tuning

☐  Run E1 on technical data from the same pretrained checkpoint as E2.

☐  Run E2 on mixed technical / general data with comparable budget and settings.

☐  Save checkpoints, logs and dataset versions; avoid tuning on the final test set.

Deliverable  E0 / E1 / E2 experiment records and checkpoints

Done when  Each run has a configuration and artifact ID; differences between E1 and E2 are intentional and documented.

Notes / blocker  ________________________________________________________________________________

# Days 9–10

Weekly objective: Train a domain-adapted model and compare controlled data mixtures.

## Day 9  |  Review training and validation

☐  Compare training and validation loss for signs of underfit or overfit.

☐  Inspect sample outputs from E1 and E2 on validation examples.

☐  Select checkpoints using validation only and document the selection rule.

Deliverable  Training experiment report

Done when  Checkpoint selection rule is stated; suspicious runs and deviations are explained.

Notes / blocker  ________________________________________________________________________________

Weekly notes / decisions  ________________________________________________________________________________

## Day 10  |  Compare domain and general quality

☐  Evaluate E0, E1 and E2 on technical and general sets.

☐  Compare BLEU and chrF; save per-example predictions for later error analysis.

☐  Check whether technical gains trade off against general translation quality.

Deliverable  Domain adaptation comparison

Done when  Same held-out examples and evaluation settings are used across systems; results are summarized by domain.

Notes / blocker  ________________________________________________________________________________

## Week 2 milestone

☐  At least one fine-tuned English–German model and reproducible pretrained comparison.

Milestone outcome  ☐ Met   ☐ Partially met   ☐ Not met

Carry-forward items  ________________________________________________

# Week 3

Quality evaluation and error analysis

Week objective: Build a repeatable evaluation and regression framework that explains model behavior.

Week status  ☐ Not started   ☐ In progress   ☐ At risk   ☐ Complete

Review date  ________________________________________________

Evidence / branch / report link  ________________________________________________

## Day 11  |  Add COMET

☐  Integrate COMET and pin / record metric version and model.

☐  Run all systems on the same held-out examples where feasible.

☐  Document resource needs and any missing scores.

Deliverable  BLEU, chrF and COMET evaluation pipeline

Done when  One command produces versioned metrics and saved predictions for named systems.

Notes / blocker  ________________________________________________________________________________

## Day 12  |  Check terminology and formatting

☐  Create a small technical terminology list with approved German terms.

☐  Implement terminology and preservation checks for names, numbers, units and placeholders.

☐  Manually validate false positives and limitations.

Deliverable  Terminology / formatting evaluation module

Done when  Checks run across model outputs and results can be reviewed by example.

Notes / blocker  ________________________________________________________________________________

Weekly notes / decisions  ________________________________________________________________________________

## Day 13  |  Classify translation errors

☐  Sample outputs and label semantic errors, omissions, terminology, grammar and formatting.

☐  Include meaning reversal cases such as lost negation.

☐  Store source, reference, system output, category and reviewer notes.

Deliverable  Error-analysis dataset and taxonomy

Done when  A reviewer can trace each label to a concrete example; uncertain cases are marked.

Notes / blocker  ________________________________________________________________________________

# Days 14–15

Weekly objective: Build a repeatable evaluation and regression framework that explains model behavior.

## Day 14  |  Add regression checks

☐  Create a fixed small regression set for critical meaning, terminology and format cases.

☐  Set cautious alerts for quality changes; avoid claiming a metric threshold proves quality.

☐  Run checks against baseline and fine-tuned checkpoints.

Deliverable  Automated translation quality checks

Done when  Tests are repeatable and report failures with the source and affected output.

Notes / blocker  ________________________________________________________________________________

Weekly notes / decisions  ________________________________________________________________________________

## Day 15  |  Analyze results

☐  Compare BLEU, chrF and COMET across systems and domains.

☐  Estimate paired uncertainty / confidence intervals where feasible; describe the method.

☐  Summarize errors, latency and throughput alongside quality scores.

Deliverable  Evaluation report and plots

Done when  Interpretation distinguishes measured results from inference and notes sample-size limits.

Notes / blocker  ________________________________________________________________________________

## Week 3 milestone

☐  Reproducible evaluation, quantitative results and detailed error analysis.

Milestone outcome  ☐ Met   ☐ Partially met   ☐ Not met

Carry-forward items  ________________________________________________

# Week 4

LLM comparison, human preferences and research

Week objective: Compare specialized NMT and multilingual LLM behavior under documented settings.

Week status  ☐ Not started   ☐ In progress   ☐ At risk   ☐ Complete

Review date  ________________________________________________

Evidence / branch / report link  ________________________________________________

## Day 16  |  Add an LLM baseline

☐  Select a multilingual LLM using Groq or Hugging Face inference.

☐  Write and freeze translation instructions, decoding settings and model version.

☐  Log API / local environment and latency context.

Deliverable  LLM translation baseline

Done when  The LLM produces saved translations and its model, prompt and execution context are recorded.

Notes / blocker  ________________________________________________________________________________

## Day 17  |  Compare NMT and LLM systems

☐  Run baseline MarianMT, fine-tuned MarianMT and LLM on the same held-out technical and general examples.

☐  Compare BLEU, chrF, COMET, terminology, errors and latency.

☐  Keep hosted API latency separate from local inference latency.

Deliverable  Comparative model results

Done when  Comparison states hardware / service context and uses the same examples and metric setup.

Notes / blocker  ________________________________________________________________________________

Weekly notes / decisions  ________________________________________________________________________________

## Day 18  |  Collect preferences

☐  Prepare about 50 translation pairs; blind system identity and randomize display order where feasible.

☐  Ask reviewers which output better preserves meaning; allow tie / cannot judge.

☐  Store source, candidates, chosen preference, reviewer and adjudication note.

Deliverable  Small structured preference dataset

Done when  Preference labels are traceable, documented and separated from training unless explicitly used in a development experiment.

Notes / blocker  ________________________________________________________________________________

# Days 19–20

Weekly objective: Compare specialized NMT and multilingual LLM behavior under documented settings.

## Day 19  |  Compare metric and human rankings

☐  Compare human choices with BLEU, chrF and COMET rankings for the same examples.

☐  Inspect disagreements and explain likely causes.

☐  Report reviewer count, sampling method and limitations.

Deliverable  Metric agreement analysis

Done when  Findings show agreement / disagreement with examples and avoid overgeneralizing a small sample.

Notes / blocker  ________________________________________________________________________________

Weekly notes / decisions  ________________________________________________________________________________

## Day 20  |  Run one focused follow-up

☐  Choose one additional controlled question from observed errors or preference disagreements.

☐  Use validation data for development; preserve final test set for final reporting.

☐  Consolidate experiment tables, decisions and findings.

Deliverable  Final research results and experiment summary

Done when  The follow-up has a clear comparison, controlled change and written result; if blocked, record why and summarize current evidence.

Notes / blocker  ________________________________________________________________________________

## Week 4 milestone

☐  NMT versus LLM comparison, small preference dataset and documented findings.

Milestone outcome  ☐ Met   ☐ Partially met   ☐ Not met

Carry-forward items  ________________________________________________

# Week 5

Research application and final presentation

Week objective: Package the research in a demonstrable Streamlit lab and a clear portfolio handoff.

Week status  ☐ Not started   ☐ In progress   ☐ At risk   ☐ Complete

Review date  ________________________________________________

Evidence / branch / report link  ________________________________________________

## Day 21  |  Complete the translation lab

☐  Finalize Streamlit input and output for English→German.

☐  Compare baseline NMT, fine-tuned NMT and LLM outputs where available.

☐  Show model identity, latency and preferred translation control.

Deliverable  Translation Lab tab

Done when  A new user can run a comparison and understand which system generated each result.

Notes / blocker  ________________________________________________________________________________

## Day 22  |  Add quality review and feedback

☐  Show candidate error explanations or flagged checks with source evidence.

☐  Allow a user to accept / reject potential findings.

☐  Capture reviewed preferences or annotations in a structured file / lightweight store.

Deliverable  Interactive error analysis and preference capture

Done when  User feedback is traceable and does not silently become training data.

Notes / blocker  ________________________________________________________________________________

Weekly notes / decisions  ________________________________________________________________________________

## Day 23  |  Build the results view

☐  Add dashboard views for BLEU, chrF, COMET, terminology, latency and technical/general split.

☐  Include training curves, experiment configurations and selected error examples.

☐  Run project tests; add a lightweight API only if the core demo is stable.

Deliverable  Research dashboard and test results

Done when  Dashboard values match saved research outputs; tests and any API scope are documented.

Notes / blocker  ________________________________________________________________________________

# Days 24–25

Weekly objective: Package the research in a demonstrable Streamlit lab and a clear portfolio handoff.

## Day 24  |  Freeze and report final results

☐  Run final benchmarks once with frozen checkpoints and data splits.

☐  Write methodology, findings, limitations and reproducibility instructions.

☐  Check model / dataset licenses, citations and privacy of any preference records.

Deliverable  Final research report and benchmark bundle

Done when  All reported values trace to saved predictions / configs; caveats and limitations are explicit.

Notes / blocker  ________________________________________________________________________________

Weekly notes / decisions  ________________________________________________________________________________

## Day 25  |  Publish the portfolio and present

☐  Polish README, installation steps, architecture, results and known limits.

☐  Prepare a 10–15 minute presentation and rehearse the Streamlit demo.

☐  Tag a final version and record remaining future work.

Deliverable  Finished repository, application and presentation

Done when  A reviewer can understand, reproduce and watch the main findings without undocumented setup.

Notes / blocker  ________________________________________________________________________________

## Week 5 milestone

☐  Complete interactive MVP, research report and interview-ready repository.

Milestone outcome  ☐ Met   ☐ Partially met   ☐ Not met

Carry-forward items  ________________________________________________

# Experiment tracking register

Use one row per run. Record enough detail to reproduce the comparison. Use the same pretrained checkpoint for E1 and E2, comparable training budgets, and validation-only checkpoint selection.

| ID | Question / change | Data version + split | Model / checkpoint | Key settings + seed | Artifacts / status |
| --- | --- | --- | --- | --- | --- |
| E0 baseline |  |  |  |  |  |
| E1 technical SFT |  |  |  |  |  |
| E2 mixed-domain SFT |  |  |  |  |  |
| E3 LLM baseline |  |  |  |  |  |
| E4 follow-up |  |  |  |  |  |

Run notes / deviations  ________________________________________________________________________________

________________________________________________________________________________

________________________________________________________________________________

________________________________________________________________________________

## Results comparison

| System | Domain | BLEU | chrF | COMET | Term accuracy | Latency | Notes |
| --- | --- | --- | --- | --- | --- | --- | --- |
| E0 baseline | Technical |  |  |  |  |  |  |
| E1 fine-tuned | Technical |  |  |  |  |  |  |
| E2 mixed | Technical |  |  |  |  |  |  |
| E0 baseline | General |  |  |  |  |  |  |
| E1 fine-tuned | General |  |  |  |  |  |  |
| E2 mixed | General |  |  |  |  |  |  |
| LLM | Technical |  |  |  |  |  |  |
| LLM | General |  |  |  |  |  |  |

Metric version / COMET model: ______________________________   Hardware / service: ______________________________

# Preference and error analysis log

Blind the system names and vary display order where practical. Add rows or attach a structured CSV / JSONL. Keep held-out test examples out of training and checkpoint selection.

| ID | Source / example link | A vs B systems hidden | Human choice / tie | Metric ranking | Error category / note |
| --- | --- | --- | --- | --- | --- |
| P01 |  |  |  |  |  |
| P02 |  |  |  |  |  |
| P03 |  |  |  |  |  |
| P04 |  |  |  |  |  |
| P05 |  |  |  |  |  |
| P06 |  |  |  |  |  |
| P07 |  |  |  |  |  |
| P08 |  |  |  |  |  |

Target: approximately 50 comparisons. Record reviewer count, sampling method, blinding, adjudication and limitations. Error categories: semantic, omission, terminology, grammar, formatting.

Patterns / disagreements / next experiment  ________________________________________________________________________________

________________________________________________________________________________

________________________________________________________________________________

________________________________________________________________________________

# Risks, dependencies and decisions

| Risk or dependency | Early signal | Response / decision | Owner / status |
| --- | --- | --- | --- |
| Limited compute or slow fine-tuning | Smoke run is slow; memory errors | Reduce subset / sequence length / batch size; use a GPU for main run if available; record the change. |  |
| Dataset license or quality | Unclear reuse terms; noisy alignment | Choose a documented source; inspect sample; remove duplicates; record license and filters. |  |
| Test leakage | Test examples appear in training or tuning | Freeze split manifest; deduplicate across splits; use validation only for selection. |  |
| COMET resource / access limits | Metric model cannot load or scores incomplete | Record exact version and limitation; complete BLEU / chrF first and report missing metric clearly. |  |
| LLM API / rate limit / changing model | Runs fail or model identifier changes | Cache predictions, pin identifier / prompt, record date and service context; make comparisons reproducible. |  |
| Preference reviewer availability | Fewer judgments than target | Recruit a small, transparent sample; report reviewer count and uncertainty; do not overclaim. |  |
| Scope creep into product work | UI consumes research time | Keep to the four research tabs; prioritize benchmark, findings and demo reliability. |  |
| Model / data usage restrictions | License or terms conflict with portfolio | Review and record terms before sharing weights, examples or app access. |  |

## Dependencies checklist

☐  Python environment, PyTorch and Hugging Face access

☐  Dataset source, license and storage plan

☐  Compute plan for fine-tuning and COMET

☐  Model checkpoint and inference access for baseline and LLM

☐  Streamlit environment and repository hosting

☐  Human reviewers and a simple preference collection process

Top current risk  ________________________________________________

Decision needed / by when  ________________________________________________

Owner  ________________________________________________

Decision log  ________________________________________________________________________________

________________________________________________________________________________

________________________________________________________________________________

# Scope guardrails and final submission

## Optional or future scope

| Item | Status | Rule |
| --- | --- | --- |
| FastAPI backend | ☐ Optional / future | Only add in Week 5 if the Streamlit research demo, results and tests are already stable. |
| Docker deployment | ☐ Future | Skip unless packaging is a specific portfolio requirement and core deliverables are complete. |
| French support | ☐ Future | Keep this project to EN→DE primary and DE→EN secondary; do not add another language during the five weeks. |
| Personalized learning features | ☐ Future | Keep the app focused on research comparison, quality evaluation and human review. |
| RLHF / GRPO | ☐ Future research | Use preference data to analyze evaluation signals; full RL training is outside the five-week scope. |
| MLflow | ☐ Optional | A structured CSV / JSONL experiment register is enough if setup time would compete with research. |

## Final submission checklist

☐  README explains the research question, setup, model cards / IDs, data sources, licenses and reproduction steps.

☐  Data card describes domain, source, cleaning, split sizes and leakage safeguards.

☐  Baseline and fine-tuned checkpoints are identified; weights are shared only when terms allow.

☐  E0 / E1 / E2 configurations and run logs include seed, data version, checkpoint and compute.

☐  Final predictions and BLEU, chrF and COMET results are saved and traceable to the report.

☐  Technical and general-domain results are separate; paired uncertainty / statistical method is explained.

☐  Terminology checks, error taxonomy and representative error examples are included.

☐  LLM comparison documents model, prompt, decoding, date and local versus hosted latency context.

☐  Preference dataset is structured; reviewer count, blinding, sampling and limitations are reported.

☐  Quality regression checks and application tests run with documented outcomes.

☐  Streamlit demo shows model identity, translations, latency and research findings.

☐  Research paper is complete (target 6–10 pages) and distinguishes evidence from interpretation.

☐  Presentation is 10–15 minutes and rehearsed; demo has a fallback recording or screenshots.

☐  Repository is clean, final version is tagged, and remaining work is documented as future scope.

Final status  ☐ Ready to share   ☐ Needs revision

Repository URL  ________________________________________________

Demo URL / run instructions  ________________________________________________

Final review date  ________________________________________________

Handoff notes  ________________________________________________________________________________

________________________________________________________________________________

________________________________________________________________________________